## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Admin | Designing Of Site | I Can Design The Site | 1 | Neha Modi | 2018-09-04
1 | SB1/US2 | Customer | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail | 1 | Shivani Bansal | 2018-09-04
1 | SB1/US3 | Seller | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail | 1 | Shivani Bansal | 2018-09-04
1 | SB1/US4 | Delivery Boy | Register Myself Using Mail Id | I Can Receive A Confirmation/Verification Mail | 1 | Shivani Bansal | 2018-09-04
1 | SB1/US5 | Customer | Receive A Confirmation Mail | My Account will be created | 1 | Shivani Bansal | 2018-09-04
1 | SB1/US6 | Seller | Receive A Confirmation Mail | My Account will be created | 1 | Shivani Bansal | 2018-09-04
1 | SB1/US11 | Delivery Boy | Receive A Confirmation Mail | My Account will be created | 1 | Shivani Bansal | 2018-09-04
1 | SB2/US1 | Customer | Modify The Account Password | I Can Keep My Account Secure | 1 | Shivani Bansal | 2018-09-12
1 | SB2/US2 | Customer | Add Product to the cart | I Can Add The Products That I want To Add into Cart | 1 | Shivani Bansal | 2018-09-12
1 | SB2/US3 | Customer | See My Delivery Charges | I Can See My Delivery Charges | 1 | Shivani Bansal | 2018-09-18
1 | SB2/US4 | Customer | Do the payment | I Can do the payment for my order | 1 | Shivani Bansal | 2018-09-18
1 | SB2/US5 | Customer | Choose the payment type | I can choose the payment type | 1 | Shivani Bansal | 2018-09-18
1 | SB2/US6 | Customer | Edit the profile | I can Edit my profile | 1 | Shivani Bansal | 2018-09-18
1 | SB3/US1 | Customer | Give Feedback/Suggestions | I give the feedback | 1 | Shivani Bansal | 2018-09-18
1 | SB3/US2 | Seller | Give The Discounts | I Can give the discounts | 1 | Shivani Bansal | 2018-09-18
2 | SB3/US3 | Customer | Apply the Promocode | I Can apply the promocode | 1 | Shivani Bansal | 2018-09-18
2 | SB3/US4 | Customer | Add the Product to wishlist | I Can Add The Product to wishlist | 1 | Shivani Bansal | 2018-09-18
2 | SB3/US5 | Customer | Share The Product | I Can Share the Product Link to other Users | 1 | Shivani Bansal | 2018-09-18
2 | SB3/US6 | Customer | Move the Product to cart from wishlist | I Can Move The Product to cart from wishlist | 1 | Shivani Bansal | 2018-09-18
2 | SB4/US1 | Admin | No Of Users Buying The Products | I Can See No of Users Buying The Products | 1 | Neha Modi | 2018-09-18
2 | SB4/US2 | Admin | Fire Delete Queries | I can Delete The Seller or Delivery That I want To Delete | 1 | Neha Modi | 2018-09-18
2 | SB4/US3 | Seller | View The Users Buying The Products | I Can View The Users Buying That Products | 1 | Shivani Bansal | 2018-09-18
2 | SB4/US4 | Seller | View The Frequently Buying Products | I Can Keep A Check On Frequently Buying Products | 1 | Shivani Bansal | 2018-09-18
2 | SB1/US7 | Admin | Fire Insert Queries | I Can add Seller In the Site. | 2 | Neha Modi | 2018-09-12
2 | SB1/US8 | Seller | Add The Products | I Can Add The Products That I want To Sell | 2 | Shivani Bansal | 2018-09-12
2 | SB1/US9 | Seller | Features Of Ptoduct | I Can Add The Features Of Product | 2 | Shivani Bansal | 2018-09-12
2 | SB1/US10 | Seller | Price Of Product | I Can Add The Price Of Product | 2 | Shivani Bansal | 2018-09-12
2 | SB1/US12 | Customer | View The Products | I Can See The Products | 2 | Shivani Bansal | 2018-09-12
3 | SB1/US13 | Customer | Search The Products | I Can Search The Products | 2 | Shivani Bansal | 2018-09-12
3 | SB2/US7 | Delivery Boy | Receive The SMS Of Placing Order | I Can Receive The SMS From User | 2 | Shivani Bansal | 2018-09-18
3 | SB2/US8 | Delivery Boy | Update The Order Details | I Can Update The Order Details | 2 | Shivani Bansal | 2018-09-18
3 | SB3/US7 | Admin | Fire Select Queries | I Can See The Details Of Seller | 2 | Neha Modi | 2018-09-18
3 | SB4/US5 | Seller | Modify The Product Details | I can Attract The Customers | 2 | Shivani Bansal | 2018-09-18
3 | SB4/US6 | Admin | Take Backup | I Can Save The Old Records In The Database For Future Use | 2 | Neha Modi | 2018-09-18
3 | SB4/US7 | Admin | Delete Backup | I Can Delete The Records Which Is Not Needed Any More | 2 | Neha Modi | 2018-09-18
3 | SB1/US14 | Admin | Modify The Account Password | I Can Keep My Account Secure | 3 | Neha Modi | 2018-09-12
4 | SB1/US15 | Seller | Modify The Account Password | I Can Keep My Account Secure | 3 | Shivani Bansal | 2018-09-12
4 | SB2/US9 | Customer | Track The Order | I Can Track The Order | 3 | Shivani Bansal | 2018-09-18
4 | SB2/US10 | Delivery Boy | Track The Location | I can Location Of User | 3 | Shivani Bansal | 2018-09-18
4 | SB3/US8 | Admin | No Of Users Visiting The Site | I Can View The No Of Users Registering | 3 | Neha Modi | 2018-09-18
4 | SB4/US8 | Admin | Modify The Site | I Can Modify The Site | 3 | Neha Modi | 2018-09-18
4 | SB2/US11 | Delivery Boy | Send Sms To User | I can Send SMS to User Of Product | 4 | Shivani Bansal | 2018-09-18
4 | SB2/US12 | Delivery Boy | Send Mail To User | I Can Send Mail To User of Product. | 4 | Shivani Bansal | 2018-09-18
4 | SB2/US13 | Delivery Boy | Call The User | I Can Call User by Mobile So that User Can receive product | 4 | Shivani Bansal | 2018-09-18
4 | SB4/US9 | Seller | Fix The Delivery Charges | I can Fix the delivery charges according to location | 4 | Shivani Bansal | 2018-09-18
4 | SB4/US10 | Customer | Login Through google,facebook | I Can place my order by login through google and facebook | 4 | Shivani Bansal | 2018-09-18

## SprintBacklog1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - BAZAARAM
SB1/US1 | Designing of site | SB1/D1/T1 | To select the layout of site | Neha Modi | In progress | 2018-09-04
|  | SB1/D1/T2 | To divide the layout of site | Neha Modi | In progress | 2018-09-04
|  | SB1/D1/T3 | To make site attractive | Neha Modi | In progress | 2018-09-04
|  | SB1/D1/T4 | To make xml files | Neha Modi | Started | 2018-09-04
|  | SB1/D1/T5 | To do the coding | Neha Modi | Started | 2018-09-04
|  | SB1/D1/T6 | To check the debugging | Neha Modi | Started | 2018-09-04
SB1/US2 | Registration of customer | SB1/D2/T1 | Email Address | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D2/T2 | Full Name | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D2/T3 | Password | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D2/T4 | Gender | Shivani Bansal | Not Started | 2018-09-04
SB1/US3 | Registration of seller | SB1/D3/T1 | Email Address | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D3/T2 | Full Name | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D3/T3 | Password | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D3/T4 | Gender | Shivani Bansal | Not Started | 2018-09-04
SB1/US4 | Registration of delivery boy | SB1/D4/T1 | Email Address | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D4/T2 | Full Name | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D4/T3 | Password | Shivani Bansal | Not Started | 2018-09-04
|  | SB1/D4/T4 | Gender | Shivani Bansal | Not Started | 2018-09-04
SB1/US5 | Receive a confirmation mail of customer | SB1/D5/T1 | verify itself | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D5/T2 | receive the notifications | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D5/T3 | receive the discounts | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D5/T4 | aware about new Products | Shivani Bansal | Not Started | 2018-09-12
SB1/US6 | Receive a confirmation mail of seller | SB1/D6/T1 | verify itself | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D6/T2 | add the new products | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D6/T3 | add the price | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D6/T4 | add the features of products | Shivani Bansal | Not Started | 2018-09-12
SB1/US11 | Receive a confirmation mail of delivery boy | SB1/D7/T1 | verify itself | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D7/T2 | receive the notification of seller | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D7/T3 | deliver the order | Shivani Bansal | Not Started | 2018-09-12
|  | SB1/D7/T4 | track the location | Shivani Bansal | Not Started | 2018-09-12
SB1/US7 | Fire insert queries by admin | SB1/D8/T1 | write the query | Neha Modi | Not Started | 2018-09-18
|  | SB1/D8/T2 | add seller | Neha Modi | Not Started | 2018-09-18
|  | SB1/D8/T3 | add delivery boy | Neha Modi | Not Started | 2018-09-18
|  | SB1/D8/T4 | keep a check on site | Neha Modi | Not Started | 2018-09-18
SB1/US8 | Products Added by seller | SB1/D9/T1 | different products are added | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D9/T2 | verify the product by admin | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D9/T3 | add the model no | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D9/T4 | actual price | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D9/T5 | discounts getting | Shivani Bansal | Not Started | 2018-09-18
SB1/US9 | Features Added Byseller | SB1/D10/T1 | size of product | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D10/T2 | colors of product | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D10/T3 | size chart of product | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D10/T4 | similar products | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D10/T5 | breif description of product | Shivani Bansal | Not Started | 2018-09-18
SB1/US10 | Price Added By seller | SB1/D11/T1 | specific price added | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D11/T2 | price of shop | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D11/T3 | price of our site | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D11/T4 | taxes | Shivani Bansal | Not Started | 2018-09-18
SB1/US12 | Customer view the products | SB1/D12/T1 | varieties of products | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D12/T2 | gender specific | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D12/T3 | color specific | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D12/T4 | price specific | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D12/T5 | discount specific | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D12/T6 | pattern specific | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D12/T7 | brand specific | Shivani Bansal | Not Started | 2018-09-18
SB1/US13 | Customer search the products | SB1/D13/T1 | by name | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D13/T2 | by brand | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D13/T3 | by gender | Shivani Bansal | Not Started | 2018-09-18
SB1/US14 | Modify the account password by seller | SB1/D14/T1 | due to security | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D14/T2 | by logging in | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D14/T3 | by click on security | Shivani Bansal | Not Started | 2018-09-18
SB1/US15 | Modify the account password by seller | SB1/D15/T1 | due to security | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D15/T2 | by logging in | Shivani Bansal | Not Started | 2018-09-18
|  | SB1/D15/T3 | by click on security | Shivani Bansal | Not Started | 2018-09-18

## SB HOURS 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 64 | 64 | Tasks
2018-09-12 | 50 | 64
2018-09-16 | 30 | 64
2018-09-18 | 0 | 64
Days

## SprintBacklog2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - BAZAARAM
SB2/US1 | Modify the account password by customer | SB2/D1/T1 | go to security | Shivani Bansal | Not Started | 2018-09-25
|  | SB2/D1/T2 | by logging in | Shivani Bansal | Not Started | 2018-09-25
|  | SB2/D1/T3 | by click on security | Shivani Bansal | Not Started | 2018-09-25
SB2/US2 | Add Product to cart by customer | SB2/D2/T1 | find the option cart | Shivani Bansal | Not Started | 2018-09-25
|  | SB2/D2/T2 | click on add to cart | Shivani Bansal | Not Started | 2018-09-25
|  | SB2/D2/T3 | message will be shown | Shivani Bansal | Not Started | 2018-09-25
SB2/US3 | Delivery charges will be seen by customer | SB2/D3/T1 | after adding products | Shivani Bansal | Not Started | 2018-09-25
|  | SB2/D3/T2 | charges are fixed | Shivani Bansal | Not Started | 2018-09-25
|  | SB2/D3/T3 | free delivery will be shown | Shivani Bansal | Not Started | 2018-09-25
|  | SB2/D3/T4 | delivery charges depends on order | Shivani Bansal | Not Started | 2018-09-25
SB2/US4 | Payment by customer | SB2/D4/T1 | Payment selection | Shivani Bansal | Not Started | 2018-09-28
|  | SB2/D4/T2 | benefits will be shown | Shivani Bansal | Not Started | 2018-09-28
|  | SB2/D4/T3 | COD will be valid or not | Shivani Bansal | Not Started | 2018-09-28
SB2/US5 | Payment option chosen by customer | SB2/D5/T1 | different payment option will be seen | Shivani Bansal | Not Started | 2018-09-28
|  | SB2/D5/T2 | select the payment option | Shivani Bansal | Not Started | 2018-09-28
|  | SB2/D5/T3 | apply the card details if it credit/debit is chosen | Shivani Bansal | Not Started | 2018-09-28
|  | SB2/D5/T4 | add the password or id if net banking is chosen | Shivani Bansal | Not Started | 2018-09-28
SB2/US6 | Edit the Profile by customer | SB2/D6/T1 | edit mobile no | Shivani Bansal | Not Started | 2018-09-28
|  | SB2/D6/T2 | edit email address | Shivani Bansal | Not Started | 2018-09-28
|  | SB2/D6/T3 | edit name | Shivani Bansal | Not Started | 2018-09-28
|  | SB2/D6/T4 | add the features of products | Shivani Bansal | Not Started | 2018-09-28
SB2/US7 | Receive the SMS of placing order by delivery boy | SB2/D7/T1 | once order will be confirmed | Shivani Bansal | Not Started | 2018-10-02
|  | SB2/D7/T2 | then connected through API | Shivani Bansal | Not Started | 2018-10-02
|  | SB2/D7/T3 | SMS will be sent to customer | Shivani Bansal | Not Started | 2018-10-02
|  | SB2/D7/T4 | order details will be checked | Shivani Bansal | Not Started | 2018-10-02
SB2/US8 | Update the order details by delivery boy | SB2/D8/T1 | order details will be updated | Shivani Bansal | Not Started | 2018-10-02
|  | SB2/D8/T2 | order details will be seen by customer | Shivani Bansal | Not Started | 2018-10-02
|  | SB2/D8/T3 | database connected | Shivani Bansal | Not Started | 2018-10-02
SB2/US9 | Order will be tracked by customer | SB2/D9/T1 | click on tracking details | Shivani Bansal | Not Started | 2018-10-05
|  | SB2/D9/T2 | different option will be shown | Shivani Bansal | Not Started | 2018-10-05
|  | SB2/D9/T3 | clicked option details will be shown | Shivani Bansal | Not Started | 2018-10-05
SB2/US10 | location will be tracked by delivery boy | SB2/D10/T1 | connected through google API | Shivani Bansal | Not Started | 2018-10-05
|  | SB2/D10/T2 | location will be tracked that is entered by user | Shivani Bansal | Not Started | 2018-10-05
SB2/US11 | SMS sent to customer | SB2/D11/T1 | SMS will be sent to customer | Shivani Bansal | Not Started | 2018-10-07
|  | SB2/D11/T2 | sent through SMS API | Shivani Bansal | Not Started | 2018-10-07
SB2/US12 | Send mail to customer | SB2/D12/T1 | mail API will be connected | Shivani Bansal | Not Started | 2018-10-07
|  | SB2/D12/T2 | mail sent to customer | Shivani Bansal | Not Started | 2018-10-07
|  | SB2/D12/T3 | mail id will be checked through user given details | Shivani Bansal | Not Started | 2018-10-07
SB2/US13 | Call the customer | SB2/D13/T1 | check the mobile no | Shivani Bansal | Not Started | 2018-10-07
|  | SB2/D13/T2 | call the customer | Shivani Bansal | Not Started | 2018-10-07
|  | SB2/D13/T3 | customer take the order | Shivani Bansal | Not Started | 2018-10-07

## SB HOURS 02
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 45 | 45 | Tasks
2017-09-28 | 15 | 45
2017-10-02 | 15 | 45
2017-10-05 | 10 | 45
2017-10-07 | 0 | 45
Days

## SprintBacklog3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - BAZAARAM
SB3/US1 | Give feedback/suggestion by customer | SB3/D1/T1 | once order will be delivered | Shivani Bansal | Not Started | 2018-10-16
|  | SB3/D1/T2 | message of feedback sent | Shivani Bansal | Not Started | 2018-10-16
|  | SB3/D1/T3 | feedback will be given | Shivani Bansal | Not Started | 2018-10-16
SB3/US2 | Give the discounts by admin | SB3/D2/T1 | by seeing past orders | Neha Modi | Not Started | 2018-10-16
|  | SB3/D2/T2 | depends if it is sale time | Neha Modi | Not Started | 2018-10-16
SB3/US3 | Promocode will be applied by customer | SB3/D3/T1 | promocode will be shown | Shivani Bansal | Not Started | 2018-10-16
|  | SB3/D3/T2 | promocode will be applied | Shivani Bansal | Not Started | 2018-10-16
|  | SB3/D3/T3 | discount will be shown | Shivani Bansal | Not Started | 2018-10-16
SB3/US4 | Product added to wishlist by customer | SB3/D4/T1 | click on move | Shivani Bansal | Not Started | 2018-10-18
|  | SB3/D4/T2 | message will be shown | Shivani Bansal | Not Started | 2018-10-18
|  | SB3/D4/T3 | see the wishlist | Shivani Bansal | Not Started | 2018-10-18
SB3/US5 | Share the product by customer | SB3/D5/T1 | share option will be shown | Shivani Bansal | Not Started | 2018-10-18
|  | SB3/D5/T2 | select the share option | Shivani Bansal | Not Started | 2018-10-18
|  | SB3/D5/T3 | click on share option | Shivani Bansal | Not Started | 2018-10-18
|  | SB3/D5/T4 | product will be shared | Shivani Bansal | Not Started | 2018-10-18
SB3/US6 | Product move to cart from wishlist by customer | SB3/D6/T1 | option will shown in the cart | Shivani Bansal | Not Started | 2018-10-23
|  | SB3/D6/T2 | click on option | Shivani Bansal | Not Started | 2018-10-23
|  | SB3/D6/T3 | add the product to cart | Shivani Bansal | Not Started | 2018-10-23
|  | SB3/D6/T4 | product added will be shown | Shivani Bansal | Not Started | 2018-10-23
SB3/US7 | Fire select queries by admin | SB3/D7/T1 | write the query | Neha Modi | Not Started | 2018-10-23
|  | SB3/D7/T2 | query will be applied | Neha Modi | Not Started | 2018-10-23
|  | SB3/D7/T3 | details will be shown | Neha Modi | Not Started | 2018-10-23
SB3/US8 | No of users visiting the site by admin | SB3/D7/T1 | write the query | Neha Modi | Not Started | 2018-10-23
|  | SB3/D7/T2 | query will be applied | Neha Modi | Not Started | 2018-10-23
|  | SB3/D7/T3 | details will be shown | Neha Modi | Not Started | 2018-10-23

## SB HOURS 03
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Incompleted Task
2018-10-16 | 25 | 25 | Tasks
2018-10-18 | 20 | 25
2018-10-23 | 0 | 25
Days

## SprintBacklog4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - BAZAARAM
SB4/US1 | No Of users buying the products by seller | SB4/D1/T1 | write the query | Shivani Bansal | Not Started | 2019-01-10
|  | SB4/D1/T2 | query will be applied | Shivani Bansal | Not Started | 2019-01-10
|  | SB4/D1/T3 | details will be shown | Shivani Bansal | Not Started | 2019-01-10
SB4/US2 | Fire Delete Queries by admin | SB4/D2/T1 | write the query | Neha Modi | Not Started | 2019-01-10
|  | SB4/D1/T2 | query will be applied | Neha Modi | Not Started | 2019-01-10
|  | SB4/D1/T3 | details will be shown | Neha Modi | Not Started | 2019-01-10
SB4/US3 | View the Users buying the products by seller | SB4/D3/T1 | write the query | Shivani Bansal | Not Started | 2019-01-10
|  | SB4/D3/T2 | query will be applied | Shivani Bansal | Not Started | 2019-01-10
|  | SB4/D3/T3 | details will be shown | Shivani Bansal | Not Started | 2019-01-10
SB4/US4 | View the frequently buying products by seller | SB4/D4/T1 | write the query | Shivani Bansal | Not Started | 2019-01-10
|  | SB4/D4/T2 | query will be applied | Shivani Bansal | Not Started | 2019-01-10
|  | SB4/D4/T3 | details will be shown | Shivani Bansal | Not Started | 2019-01-10
SB4/US5 | Modify The Product Details by seller | SB4/D5/T1 | go to site | Shivani Bansal | Not Started | 2019-01-12
|  | SB4/D5/T2 | go to product details | Shivani Bansal | Not Started | 2019-01-12
|  | SB4/D5/T3 | modify the details | Shivani Bansal | Not Started | 2019-01-12
|  | SB4/D5/T4 | modification shown | Shivani Bansal | Not Started | 2019-01-12
SB4/US6 | Take backup by admin | SB4/D6/T1 | apply the query | Neha Modi | Not Started | 2019-01-12
|  | SB4/D6/T2 | see the different details | Neha Modi | Not Started | 2019-01-12
|  | SB4/D6/T3 | details will be shown | Neha Modi | Not Started | 2019-01-12
|  | SB4/D6/T4 | check progress site | Neha Modi | Not Started | 2019-01-12
SB4/US7 | Delete backup by admin | SB4/D7/T1 | write the query | Neha Modi | Not Started | 2019-01-12
|  | SB4/D7/T2 | query will be applied | Neha Modi | Not Started | 2019-01-12
|  | SB4/D7/T3 | details will be deleted | Neha Modi | Not Started | 2019-01-12
SB4/US8 | Modify the site by admin | SB4/D8/T1 | select the different GUI | Neha Modi | Not Started | 2019-01-15
|  | SB4/D8/T2 | modify the details | Neha Modi | Not Started | 2019-01-15
|  | SB4/D8/T3 | other details modified | Neha Modi | Not Started | 2019-01-15
SB4/US9 | Fix The Delivery Charges by seller | SB4/D9/T1 | delivery charges fixed | Shivani Bansal | Not Started | 2019-01-15
|  | SB3/D9/T2 | charges will be applied | Shivani Bansal | Not Started | 2019-01-15
|  | SB4/D9/T3 | charges will be shown | Shivani Bansal | Not Started | 2019-01-15
SB4/US10 | Login Through google,facebook by customer | SB4/D10/T1 | once order will be placed | Shivani Bansal | Not Started | 2019-01-15
|  | SB4/D10/T2 | login option will be shown | Shivani Bansal | Not Started | 2019-01-15
|  | SB4/D10/T3 | clicked option will be shown | Shivani Bansal | Not Started | 2019-01-15

## SB HOURS 04
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup | 6
|  | Search about components required | 8
|  | Purchase component from Market | 4
|  | Develop the hardware | 8
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application | 4
|  | search paint application | 6
|  | search video making application | 4
|  | search audio recording applications | 4
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials | 6
|  | Study tutorials | 8
|  | start with Basics of Java | 4
|  | start with Basics of Java | 6
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of Java | 8
|  | start with Basics of Java | 4
|  | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application | 6 |  |  | 0
|  | coding of onscreen application | 6 |  |  | 0
|  | Debug the code | 4
|  | Debug the code | 4
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen. | 4
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 8
|  | Implentation of application on virtual screen. | 6
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
|  | Switch on the projector and set the projected screen | 4
|  | Interface it with PC/laptop | 4
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen | 4
|  | Use different applications on the virtual screen | 4
|  | Check the changes made at the virtual screen | 6
|  | Checking if it is working effectively with the laptop and not damaged | 6
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables | 8
|  | Prepare all software deliverables | 6
|  | Prepare a hardware & software guide | 8
|  | Prepare a user manual & guide for the users | 6
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project | 6
|  | Project demonstration | 8
|  | Project demonstration | 4
|  | Project to be operated by different users | 4

## SB BD Ch04
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Incompleted Task
2019-01-10 | 32 | 32 | Tasks
2019-01-12 | 25 | 32
2019-01-15 | 0 | 32
Days